Summary Actions

| Implementation area | Suggested activity | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |
| --- | --- | --- | --- | --- | --- |
| Leadership and Governance | - Complete a stakeholder analysis of cancer services to identify key partners for implementation. - Implement a Trust wide ACCEND Steering Group - Write a communication plan to support implementation. - Embed it into HR, education, line management, and recruitment processes. - Create an environment that empowers staff to make ACCEND-led changes. - Recruit an ACCEND Facilitator - Provide quarterly reporting to the Alliance. |  |  |  |  |
| Role design | - Plan how you will embed ACCEND in Recruitment inductions competency development CPD planning |  |  |  |  |
| Job descriptions | - Work with their HR business partners to agree a coordinated approach to review relevant job descriptions to ensure consistency with the ACCEND Framework. |  |  |  |  |
| Appraisals | - Integrate the ACCEND Framework into appraisal processes to ensure that capability development, levels of practice, and education requirements are routinely reviewed and supported. |  |  |  |  |
| Education | - Provide clear, consistent expectations for cancer capabilities and education at supportive, assistive, registration, enhanced, advanced and consultant level roles. - Provide or enable access to a range of learning opportunities aligned to ACCEND. - Clear, equitable process for applying for CPD funding, education grants & other opportunities. - Complete an annual training needs analysis at all levels. |  |  |  |  |