Improving Black and Asian women's experiences and outcomes around breast cancer

2026-27 Action Plan

| Improvement area | Actions | Outputs / outcomes | Lead | When |
| --- | --- | --- | --- | --- |
| - Improved ethnicity recording and data sharing | - Work with Hospital Cancer Managers and others to understand how they capture and record ethnicity | Map how ethnicity data is captured in trusts Reduce the proportion of unknown ethnicity data to a maximum of 25% across all Trusts (using 45% in 2025 baseline) | Emma Leatherbarrow (EL), WCA Strategic Equality and Involvement lead | Dec 2026 |
|  | - Review ethnicity data recording and analysis within Breast Screening Teams | More accurate understanding of breast screening uptake by ethnicity and codesigned activities to address gaps in uptake | EL | May 2027 |
| - Improved culturally appropriate healthcare across Wessex | - Organise six Unseen, Unheard film showings across Dorset and Hampshire to raise awareness of Black women’s experiences of breast cancer | Number of attendees and evaluation of events Increased awareness of Black women’s experiences of breast cancer diagnosis and care | Sue Newell (SN) with Lead Breast Cancer Nurses / hospital trusts | From July 2026 |
|  | - Offer awareness raising workshops at Hampshire and Isle of Wight GP practice ‘Target’ events | Numbers of attendees and evaluation of events Increased awareness of Black women’s experiences of breast cancer diagnosis (specifically women below and above screening age) | SN with WCA GP advisors and patients | From June 2026 - 2027 |
|  | - Continue to promote available free, online training for General Practice on diagnosing breast cancer in Black women | Improved GP awareness (anecdotal feedback via Target events and WCA GPs) Reduction in late-stage cancer diagnosis Black and Asian women in Wessex | Tamzen Hogben, WCA General Practice Advisor and Christine Glew, WCA GP Breast Cancer Lead | Ongoing |
|  | - Share and promote the Macmillan Cultural Competency Training with Trust Education Leads and GP Communities of Practice | Improved access to cultural competency training and best practice sharing across organisations | Kathy Cooke, WCA Workforce Lead | Dec 2026 |
| - Enhanced awareness of breast cancer in Black and Asian communities | - Recommission and continue to promote Communities Against Cancer (CAC) to Black and Asian women and communities who want to raise awareness / become Well-Being Champions | More engaged Black and Asian women in CAC champion roles and a better understanding of the barriers they experience in accessing health / cancer services More Black and Asian are aware of the signs and symptoms of breast and other cancers | SN and Communities Against Cancer Team | Ongoing |
|  | - Within CAC proactively work with the Black, Asian and minority communities that are at higher risk of some cancers / later diagnosis | Service recommissioned Numbers of community events / community reach More Black and Asian people are aware of the signs and symptoms of cancer, prevention messaging and advice seeking | SN/EL | Jan 2027 |
|  | - Work in Dorset to improve uptake of breast (and other screening) with Black, Asian and minority communities | Baseline ethnicity data established Increased breast screening uptake by Black and Asian women | SN/EL | Mar 2028 |
|  | - Work with a Black community organisation to codesign breast cancer awareness messages for Black and Asian women under 50 years old | More culturally resonant messaging that can be shared across more local communities Increased awareness of breast cancer symptoms and where to seek advice by Black and Asian women | SN | Mar 2027 |
|  | - Co-design approach to survivorship patient storytelling with Black and Asian women to support awareness raising activities | Stories available to be shared widely Increased awareness of breast cancer symptoms, where to see advice and survivorship by Black and Asian women | SN with Anastasia Lungu-Mulenga HIOW Healthcare NHS Foundation Trust | Mar 2027 |
|  | - Explore how WCA can support the Hampshire and Isle of Wight Healthcare NHS Trust self-advocacy project | Options identified for WCA support Outcomes to be developed alongside project | SN with AL-M | Mar 2027 |
|  | - Explore good practice and work with communities to widen access to research, genetic testing and understanding family history that is culturally aware | Good practice identified and initiated local community conversations about what might work Increased participation in research Increased participation in genetic testing | Anne Croudass, WCA Research Clinical Advisor Becky Foster, Research Fellow, University of Southampton | Mar 2027 |
|  | - Explore funding to support the impact evaluation of community awareness raising activities | Evaluation undertaken with robust evidence of impact | EL | Dec 2026 |
| - Getting the practicalities of good cancer care for Black and Asian women right | - Explore funding options with Dorset REC/Wessex Cancer Support to help identify support needs for people from minoritised communities who are affected by cancer | Funding sourced and needs assessment completed so that we have a better understanding of needs to inform service development People from minoritised communities can access support that meets their needs | SN | Dec 2026 |
|  | - Identify local and national good practice in terms of providing practical support to Black and Asian breast cancer patients, including wigs, prosthetics and imagery to share across Wessex | Good practice mapping complete and shared to inform commissioning / service planning, including exploring innovative solutions such as cultural navigators Improved access to culturally appropriate practical support | SN | Mar 2027 |
|  | - Work with Breast Care Nurses and Black and Asian breast cancer patients to understand recent patient experiences of practical support and the impact of improvement activities | Better understanding of what’s working and identify other improvement areas Outcomes to be developed alongside project | SN | Mar 2027 |
|  | - Work with Black and Asian breast cancer patients to ensure their experience of patient stratified follow up (PSFU) meets their needs | Better understanding of how PSFU currently meets the needs of Black and Asian women and what changes might be required Patients are put on the right follow up pathway and experience of follow up for Black and Asian women improves | TBA | June 2027 |
|  | - Explore with Breast Clinical Advisory Group whether to implement Project Brave (image-based mastectomy decision-making tool) | Brave shared across Trusts to aid shared decision-making Improved patient confidence to make the right decisions for them with their clinical team | EL | Oct 2026 |

For more information, questions or to get involved contact: Sue Newell, Wessex Cancer Alliance on 07961 062883 or Sue.Newell@wca.uhs.nhs.uk.

For background information to this work visit: https://wessexcanceralliance.nhs.uk/black-and-asian-women-and-breast-cancer/